RPSU -  MUSANZE COLLEGE / ARBITRATION COMMITTEE ACTION PLAN/ ACADEMIC YEAR 2025 - 2026

| No | Activity | Problem Identified | Proposed Solution | Resources Needed | Budget | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | One-Day Training for Class Representatives + Lecture by Lawyer & College Counselor | Class representatives lack teamwork, conflict-resolution skills, and legal understanding of arbitration procedures. | Conduct a combined 1-day workshop for 104 class representatives, including: - Teamwork & leadership training - Conflict resolution skills - Understanding RP laws, student rights, and arbitration procedures (delivered by a lawyer & counselor) | - Snacks (Fanta + cake + egg) - Training materials (books, markers, handouts) - Venue setup - Invitations for Lawyer & Counselor | Snacks:(2000Frw X 104)= 208,000Frw | February 2026 |
| 2 | Know Your Laws” – RP Student Handbook Awareness Videos: Produce 17 educational video episodes, each handled by a committee member. | Goal: To help the panel members clearly understand RP rules and confidently explain them to students. | - Each episode covers one section of the RP Student Handbook - Use simple explanations + examples - Create a panel training session before recording - Publish episodes throughout the year | Volunteers, Recording tools, Editing laptop | 00.00 | Throughout the academic year |
| 3 | Maintenance of 5 Polling Boxes | Old polling boxes need repairs and fresh paint to ensure security and election credibility. | Repair, repaint, and apply necessary materials to 5 boxes. | Paint, ink, labor, repair materials | 10,000 Frw * 5 = 50,000 Frw | Before elections |
| 4 | Install a secure new suggestion box. | Students lack a safe and private way to submit suggestions or concerns. | Purchase and install a locked suggestion box at the office. | New suggestion box + locker | 15,000 Frw | Immediately after approval |
| General Election |  |  |  |  |  |  |

| No | Item Needed | Quantity / Formula | Amount (Frw) |
| --- | --- | --- | --- |
| 1. | Ream of papers | 1 | 8000 Frw |
| 2. | Pens | 1 Box | 5000 Frw |
| 3. | Printing cost | 50 X Around 200 Voters | 10000 Frw |
| 4. | Markers | 5 X 500 Frw | 5000 Frw |

Swearing-In & Handover Ceremony

| Activity: Organize a full ceremony for handing over leadership and recognizing contributions. Key Notes: - Invite guild presidents from neighboring colleges - Invite former Guild Council members (2020–2024) - Performance from College troupe - Performance of invited singers - Other Activities related to preparations will be discussion during preparations of ceremony. | Resources Needed & Budget: - Certificates (80 × 2,000 Frw) = 160,000 Frw - T-shirts for new committee (17 × 15,000) = 255,000 Frw - Paper serviettes (3 × 500) = 1,500 Frw - Symbolic Guild Council 5-Year Anniversary Cake = 20,000 Frw - Champagne = 10,000 Frw - Water for ceremony (5 boxes × 5,000) = 25,000 Frw - Hiring a restaurant (80 people × 5,000 Frw) = 400,000 Frw |
| --- | --- |

TOTAL BUDGET = 1,172,500 Frw

Prepared By: Arbitration Committee on November 28, 2025

MUHORAKEYE Diane – President of Arbitration Committee